## Backlog
Product Backlog - Campus Placement & Internship Pipeline
Prajwal G Devadiga ¦ PES1UG24CS590 ¦ Problem Statement #03 ¦ Campus & Academic Operations
1 Epics ¦ 6 User Stories ¦ 34 points total ¦ Sprint 1 = 21 ¦ Sprint 2 = 13 ¦ backlog = 0
Epic | Story ID | Story Title | As a ... | I want to ... | So that ... | Priority | Story Points | Sprint | Traces to | Planning Poker
EPIC-1 Drive Application & Eligibility Screening | US-1.1 | Upload & Parse Resume | student applicant | upload my resume as a PDF and have my skill tags extracted from it automatically | I am matched to relevant drives without re-typing or tagging my own profile | High | 8 | CPIP Sprint 1 | FR-001 | Spread 5 / 8 / 13, settled at 8 - the upload itself is trivial; resumes have no fixed layout, so parsing accuracy is the real unknown rather than the coding effort.
EPIC-1 Drive Application & Eligibility Screening | US-1.2 | Create a Corporate Drive | placement officer | create a drive with the role, CTC band and an application window | students can see the opportunity and apply to it | High | 5 | CPIP Sprint 1 | FR-002 | Spread 3 / 5, settled at 5 - the form is simple, but the window needs timezone-safe open and close handling and that is where the 3 was too optimistic.
EPIC-1 Drive Application & Eligibility Screening | US-1.3 | Configure Multi-Tier Eligibility | placement officer | set minimum CGPA, maximum active backlogs, permitted branches and a prior-offer cap on a drive | ineligible students are screened out automatically instead of by hand | High | 8 | CPIP Sprint 1 | FR-002 | Spread 5 / 8 / 8, settled at 8 - four independent rule tiers that must compose, and each one has to stay individually explainable when it is the tier that fails.
EPIC-1 Drive Application & Eligibility Screening | US-1.4 | See Eligibility Status per Drive | student applicant | see whether I am eligible for each drive and exactly which rule I fail | I can contest a stale academic record instead of guessing why I was filtered out | Medium | 5 | CPIP Sprint 2 | FR-001, FR-003 | Spread 3 / 5, settled at 5 - rendering the list is easy; surfacing a per-tier reason for every failure is what makes the screen worth building.
EPIC-1 Drive Application & Eligibility Screening | US-1.5 | Apply to an Eligible Drive | student applicant | apply to a drive I am eligible for before its application window closes | I am considered by the visiting company | High | 5 | CPIP Sprint 2 | FR-003 | Unanimous 5, and probably wrong - nobody raised that the submit path has to re-run the whole US-1.3 rule set at submission time, which makes it larger than it looked.
EPIC-1 Drive Application & Eligibility Screening | US-1.6 | Enforce the Application Window | placement officer | late applications refused automatically with a clear reason code | the shortlist we hand the company is final and needs no manual reconciliation | Medium | 3 | CPIP Sprint 2 | FR-003 | Spread 2 / 3, settled at 3 - one server-side check, but it must read server time and never the browser clock, which is what moved it off 2.

## Epics
Epic | Title | Description | Traces to | Points
EPIC-1 | Drive Application & Eligibility Screening | Take a student from a published corporate drive to a submitted, screened application: publish the drive with its eligibility rule set, parse the student's resume, show them exactly where they stand against each rule, and let eligible students apply before the window closes. | FR-001, FR-002, FR-003 | 34

## Sprints
CPIP Sprint 1 | 21 pts | 3 stories
Goal | A placement officer can publish a drive carrying its full eligibility rule set, and a student has a parsed profile for those rules to be evaluated against.
Story | Title | Priority | Points
US-1.1 | Upload & Parse Resume | High | 8
US-1.2 | Create a Corporate Drive | High | 5
US-1.3 | Configure Multi-Tier Eligibility | High | 8
CPIP Sprint 2 | 13 pts | 3 stories
Goal | A student can see exactly where they stand against every published drive and submit an application while the window is still open.
Story | Title | Priority | Points
US-1.4 | See Eligibility Status per Drive | Medium | 5
US-1.5 | Apply to an Eligible Drive | High | 5
US-1.6 | Enforce the Application Window | Medium | 3